## Sheet1
Workflow Diagram – Showing how a project moves through the system. | Quotation (Q)
│
▼
Live Quote (LQ)
│
▼
Survey & Drawings
│
▼
Ready for Production
│
▼
Manufacturing (MFG)
│
▼
Collection / Delivery / Installation
│
▼
Commissioning
│
▼
AST Asset Created
│
▼
Asset Profile & Life Cycle
│
▼
Service Quote (S)
│
▼
Live Service (LS)
│
▼
Lifetime Maintenance

## Index
Table of Contents
Sheet No.
Index | 1
DATA INPUT - NOTES | 2
Stage 1A - Quotations (Q) | 3
Stage 1B - Service Quotes (S) | 4
Stage 2 - Live Quote (LQ) | 5
Stage 2 - Live Service (LS) | 6
Stage 2A - Service Ops. Dashboard | 7
Stage 2B -Service Parts Distpatch | 8
Stage 3 - Survey - Drawings | 9
Stage 4A - Ready for Prod LQ | 10
Step 4B - Reday for Prod LS | 11
Stage 5 - LS or LQ MFG Tracker | 12
Stage 5 - LIVE MFG Tracker | 13
Stage 6A - Cost. Collection | 14
6B - IFS Delivery Supply Only | 15
Stage 6C - Install office View | 16
Stage 6D-Installation Field View | 17
Installation Calender | 18
AST - Asset Register | 19
Asset Profile Life Cycle | 20
Stock Control Sheet | 21
Engineer Portal | 22
Test Report Valid Dates | 23

## DATA INPUT - NOTES
1. Data Inputs – Quotations (Q)
This section defines every field required to create and manage an installation quotation.
Customer Information
Quote Number
Quote Date
Customer
Contact Name
Company
Telephone
Mobile
Email
Enquiry Source
Project Manager
Site Information
Site Name
Site Address
Site Contact
Site Telephone
Site Email
Access Notes
Project Information
Product Type
Fire Curtain / Smoke Curtain
Installation Type
Number of Systems
Standards Required
Supply Type
Estimated Installation Date
Commercial Information
Quote Value
VAT
Payment Terms
Valid Until
Probability
Status
CRM
Next Action
Next Action Date
Assigned To
Chase History
Internal Notes
Documents
Quote PDF
Drawings
Specifications
Photos
Customer Documents
Conversion
Convert to Live Service (LS)
Customer Information
Service Quote Number
Quote Date
Customer
Site
Linked Asset(s)
Site Contact
Contract Information
Service Type
Service Category
Frequency
Number of Visits per Year
SLA Level
Response Time
Contract Start Date
Contract Renewal Date
Contract Term
Renewal Type
Contract Options
Labour Included
Parts Included
Travel Included
Out of Hours Cover Included
Commercial Information
Quote Value (Ex VAT)
Quote Value (Inc VAT)
Annual Revenue
One-Off Charges
Invoice Schedule
Payment Terms
Pricing Valid Until
CRM
Status
Probability
Next Action
Next Action Date
Chase History
Notes
Documents
Service Quote PDF
Scope of Works
Site Photos
Supporting Documents
Conversion
Convert to Live Service (LS)

## Stage 1A - Quotations (Q)
Stage 1 - Quotation (Q)
Rule Q-001 – Quote Number Allocation
Rule
Every quotation must have a unique Quote Number.
Quote numbers are generated by the authorised user in accordance with the Insight Fire Solutions numbering convention.
Example:
Q260001
Q260002
Q260003
The CRM must validate that the Quote Number is unique before the quotation can be saved.
Duplicate Quote Numbers are not permitted, some quotes will have a Revised example - IFS-Q26001R1
Trigger Q-T001 – New Quote
When a user clicks Create New Quote:
The CRM shall:
Open a blank quotation record.
Prompt the user to enter the Quote Number.
Validate that the Quote Number has not already been used.
Create the audit trail.
Set the initial status to New Enquiry.
Set the default probability to 10% (editable by the user).
Validation
The Quote Number must:
Be unique.
Not already exist.
Follow the company numbering format.
Be locked after the quotation has been converted to an live quote -(LQ)
| Record | Prefix | Example
| Installation Quote | Q | Q260001
| Live Quote | LQ | LQ260001
| Service Quote | S | S260001
| Live Service | LS | LS260001
| Asset | AST | AST-LQ260001-001
| Manufacturing | MFG | MFG260001
| Collection | COL | COL260001
| Delivery | DEL | DEL260001
| Installation | OPS | OPS260001
| Service Visit | SV | SV260001
| Call Out | CO | CO260001
| Invoice | INV | INV260001
The CRM should retain the parent relationship. For example:
Q260001 → converts to LQ260001.
LQ260001 creates MFG260001.
LQ260001 creates AST-LQ260001-001, AST-LQ260001-002, AST-LQ260001-003 (one asset per installed curtain).
Future service quotes and live services can always trace back to the original installation.
That gives you a complete audit trail from the very first quote through manufacturing, installation, asset creation, servicing, repairs, and eventual replacement. It's a much stronger structure than letting each stage generate unrelated numbers.

## Stage 1B - Service Quotes (S)
Data Iput - Service Quotes (S)
Rule S-001 – Service Quote Number Allocation
Every service quotation must have a unique Service Quote Number.
The Service Quote Number will be entered manually by an authorised user in accordance with the Insight Fire Solutions numbering convention.
Format example:
S-Q260001
S-Q260002
S-Q260003
Required behaviour
When a user selects Create New Service Quote, the CRM must:
open a new blank Service Quote record;
require the user to enter the Service Quote Number;
check that the number has not already been used;
prevent the record from being saved if the number is duplicated;
record who created the quote and the creation date and time;
link the quote number to all documents, notes, chase records and future service records associated with that quotation.
Validation rules
The Service Quote Number must:
be mandatory;
be unique;
follow the approved company numbering format;
not contain unapproved characters;
not be changed after conversion to a Live Service, unless changed by an Administrator;
remain permanently linked to the original Service Quote, even if the quote is later lost, cancelled or converted.
Conversion rule
When the Service Quote is converted to a Live Service (LS):
the original Service Quote Number must remain visible;
the Service Quote and Live Service must be linked;
the system must copy the customer, site, linked assets, service scope, commercial details, documents, notes and chase history into the new Live Service record;
the Live Service number must be entered or generated in accordance with the separate Live Service numbering rule.
Permissions
Service/Sales users may:
enter a new Service Quote Number;
save the quotation once the number passes validation.
Administrators may:
correct a Service Quote Number before conversion;
correct a converted number only with a reason;
view the complete change history.
Other users may not:
delete the Service Quote Number;
reuse a previously issued number;
change the number after conversion without Administrator approval.
Audit trail
The CRM must record:
Service Quote Number;
user who entered it;
date and time entered;
any previous number;
any replacement number;
reason for change;
approving Administrator;
date and time of approval.

## Stage 2 - Live Quote (LQ)
Stage 2 - Live Quotations (LQ)
Rule LQ-001 – Live Quote Number Allocation
Every Live Quotation must have a unique Live Quote Number.
The Live Quote Number will be entered by an authorised user in accordance with the Insight Fire Solutions numbering convention.
Example
LQ260001
LQ260002
LQ260003
Required Behaviour
When a quotation is converted to a Live Quote, the CRM shall:
Create a new Live Quote (LQ) record.
Prompt the user to enter the Live Quote Number.
Validate that the number is unique.
Copy all approved information from the quotation.
Link the original Quote (Q) to the new Live Quote (LQ).
Record the user, date and time of conversion.
Data Automatically Copied from Quote (Q)
Customer Information
Customer
Contact Name
Company
Telephone
Mobile
Email
Site Information
Site Name
Site Address
Site Contact
Site Telephone
Site Email
Commercial Information
Quote Value
VAT
Payment Terms -Deposit % then add -next percentage _ Let us create this add another always nett and VAT is 20% or 5% or NO Vat
Quote Documents
Internal Notes
Project Information
Product Type - FS120 / FS240 / FSPlus / SmokeSafe
Supply Type - Supply and Install / Supply Only / Supply and Deliver
Number of Systems
Standards Required - EN1634-1 or EN12101
Drawings
Specifications - control type / finish / producd type etc
Additional Data Required in Live Quote
Project Management
Project Manager
Assigned Designer
Assigned Surveyor
Assigned Contracts Manager
Installation Type
Priority
Target Installation Date
Commercial
Purchase Order Received
Contract Value
Deposit Required
Deposit Received
Outstanding Balance
Retention
Payment Milestones
Project Progress
Survey Status
Drawing Status
Customer Approval
Production Status
Manufacturing Status
Installation Status
Handover Status
Validation Rules
A Live Quote cannot be created unless:
Customer exists.
Site exists.
Quote status = Order Placed.
Quote Number exists.
Project Owner is assigned.
The Live Quote Number must:
Be unique.
Be mandatory.
Follow the company numbering convention.
Not be changed after production has started unless authorised by an Administrator.
Permissions
Sales Team
Can:
Create Live Quotes.
Edit commercial information.
Upload documents.
Cannot:
Delete Live Quotes.
Change completed project stages.
Contracts Team
Can:
Edit project information.
Allocate project resources.
Progress stages.
Cannot:
Delete commercial records.
Accounts
Can:
Update payment status.
Approve deposits.
Approve accounts release.
Cannot:
Edit technical project information.
Administrator
Full access.
Audit Trail
The CRM must record:
Live Quote Number.
Original Quote Number.
User who converted the project.
Date and time of conversion.
All status changes.
All document uploads.
All payment updates.
All project stage changes.
Any manual amendments.

## Stage 2 - Live Service (LS)
Stage 2 - Live Service (LS)
Purpose
The Live Service (LS) is the operational record created when a Service Quote (S) has been accepted by the customer.
It becomes the central service management record, tracking contract information, engineer scheduling, service visits, maintenance history, components used, compliance documentation and recurring service activities throughout the life of the contract.
Rule LS-001 – Live Service Number Allocation
Every Live Service must have a unique Live Service Number.
The Live Service Number will be entered by an authorised user in accordance with the Insight Fire Solutions numbering convention.
Example
LS260001
LS260002
LS260003
Required Behaviour
When a Service Quote is converted to a Live Service, the CRM shall:
Create a new Live Service (LS) record.
Prompt the user to enter the Live Service Number.
Validate that the number is unique.
Copy all approved information from the Service Quote.
Link the original Service Quote (S) to the new Live Service (LS).
Record the user, date and time of conversion.
Data Automatically Copied from Service Quote (S)
Customer Information
Customer
Contact Name
Company
Telephone
Mobile
Email
Site Information
Site Name
Site Address
Site Contact
Site Telephone
Site Email
Site Access Information
Contract Information
Service Type
Service Frequency
SLA
Contract Value
Renewal Date
Payment Terms
Scope of Works
Linked Assets
Asset Number(s)
Product Type
System Manufacturer
System Location
Number of Systems
Documents
Service Quote
Scope of Works
Previous Service Records
Site Photos
Customer Documents
Additional Data Required in Live Service
Service Management
Service Manager
Assigned Engineer
Service Status
Priority
Next Service Date
Service Due Date
Engineer Allocation
Planned Visit Date
Commercial
Contract Status
Annual Revenue
Outstanding Balance
Renewal Status
Invoice Status
Operational
RAMS Status
Parts Required
Van Stock Required
Purchase Requirements
Service Report
Engineer Notes
Customer Signature
Validation Rules
A Live Service cannot be created unless:
Customer exists.
Site exists.
At least one linked Asset exists (or is identified if it's a first service).
Service Quote status = Order Placed.
Service Manager is assigned.
The Live Service Number must:
Be unique.
Be mandatory.
Follow the company numbering convention.
Not be changed once service visits have been recorded unless authorised by an Administrator.
Permissions
Service Team
Can:
Create Live Services.
Schedule engineers.
Upload service documents.
Complete service records.
Cannot:
Delete Live Services.
Edit completed service history.
Operations
Can:
Allocate engineers.
Schedule visits.
Upload RAMS.
Manage parts.
Accounts
Can:
Update invoice status.
Record payments.
Manage contract values.
Administrator
Full access.
Audit Trail
The CRM must record:
Live Service Number.
Original Service Quote Number.
User who converted the service.
Date and time of conversion.
Engineer allocations.
Service visit history.
Parts used.
Documents uploaded.
Status changes.
Contract renewals.
All manual amendments.
This mirrors the Live Quote structure, making the specification consistent. The difference is that LQ manages projects, whereas LS manages ongoing service contracts, engineer visits and maintenance throughout the asset's lifecycle.

## 2A Service Ops. Dashboard
Service Operations Dashboard | Service Operations Dashboard
Purpose
The Service Operations Dashboard shall provide a central management system for all service-related activities, including planned preventative maintenance (PPM), reactive call-outs, repairs, warranty visits, surveys and remedial works.
The dashboard shall provide the Office Team with real-time visibility of engineer activities, service schedules, project progress, outstanding actions and commercial status.
Dashboard Summary
The dashboard shall display live statistics, including:
Engineers On Site Today
Jobs Scheduled Today
Jobs In Progress
Jobs Completed Today
Jobs Awaiting Engineer Allocation
Emergency Call-Outs
Outstanding Service Reports
Warranty Visits
Survey Visits
Return Visits
Repairs Awaiting Parts
Parts Ordered
Outstanding Customer Quotations
Outstanding Service Invoices
Service Calendar
The dashboard shall integrate directly with the Service Calendar and display:
Today's Jobs
Tomorrow's Jobs
Upcoming Jobs
Overdue Jobs
Engineer Availability
Return Visits
Annual Maintenance Visits
Engineer Activity
The Office Team shall be able to view:
Engineer Name
Current Job
Job Status
Estimated Completion Time
Last CRM Update
Photographs Uploaded
Service Report Submitted
Site Issues Raised
Live Job Status
Each service job shall display:
Service Number
Customer
Site Address
System Type
Engineer Assigned
Service Type
Current Status
Service Status
Dropdown:
Scheduled
Engineer Travelling
On Site
Service In Progress
Awaiting Parts
Awaiting Customer Approval
Return Visit Required
Complete
Cancelled
Service Types
The dashboard shall categorise jobs as:
Planned Preventative Maintenance (PPM)
Reactive Call-Out
Repair
Warranty
Survey
Commissioning
Battery Replacement
Charger Replacement
Emergency Attendance
Other
Parts Management
The dashboard shall identify:
Parts Required
Parts Ordered
Parts Awaiting Delivery
Parts Allocated
Parts Collected
Parts Fitted
The Office Team shall be notified when parts are delaying completion.
Outstanding Actions
The dashboard shall highlight:
Reports Not Submitted
Customer Sign-Off Missing
Photographs Outstanding
Return Visits Required
Parts Awaiting Delivery
Quotations to Raise
Invoices to Raise
Warranty Claims
Customer Complaints
Commercial Information
The Office Team shall be able to view:
Service Value
Parts Cost
Labour Cost
Warranty Status
Chargeable / Non-Chargeable
Quote Required
Invoice Status
Outstanding Balance
This information shall not be visible to engineers.
Document Status
The dashboard shall indicate whether the following have been completed:
Service Report
Call-Out Report
Repair Report
Photographs
Customer Signature
Parts Record
Recommendations
Quotation Required
Follow-Up Visit
Automatic Workflow Triggers
The CRM shall automatically create tasks when:
A service report has not been submitted.
A customer signature is missing.
A return visit is required.
Parts need to be ordered.
A quotation is required for remedial works.
An invoice is ready to be raised.
A warranty claim has been identified.
Dashboard Filters
The dashboard shall allow filtering by:
Engineer
Customer
Site
Service Type
Status
Date
Region
Warranty
Chargeable / Non-Chargeable
Permissions
Service Office Team
Can:
Schedule service visits.
Allocate engineers.
View all service jobs.
Raise quotations.
Order parts.
Review reports.
Schedule return visits.
Raise invoices.
Service Engineers
Can:
View assigned jobs.
Update progress.
Complete service forms.
Upload photographs.
Submit reports.
Cannot:
View commercial information.
Raise invoices.
Amend pricing.
View customer quotations.
Management
Can:
View all jobs and engineers.
Monitor KPIs and workload.
Review profitability.
Reallocate resources.
Override schedules.
Dashboard KPIs
The dashboard shall provide management reporting, including:
Services Completed This Week
Average Response Time
First-Time Fix Rate
Return Visit Percentage
Warranty vs Chargeable Visits
Outstanding Quotations
Outstanding Invoices
Engineer Utilisation
Average Service Duration
Parts Spend
Revenue by Service Type
Audit Trail
The CRM shall record:
Engineer allocations.
Status changes.
Service report submissions.
Photograph uploads.
Customer signatures.
Parts ordered and fitted.
Quotations raised.
Invoices triggered.
User making each change.
Date and time of every activity.
Integration
The Service Operations Dashboard shall integrate with:
Service Calendar – scheduling and engineer allocation.
Engineer Portal (Field View) – live engineer updates, forms and photographs.
Parts & Inventory – stock allocation and ordering.
Accounts – quotation and invoice triggers.
Asset Register – service history linked to each curtain/system.
Customer Portal (future enhancement) – allowing customers to view service reports and maintenance history.
This gives your office a live operational dashboard for all service work, ensuring nothing is missed—from engineer allocation and parts management through to quotations, invoicing and follow-up actions.

## 2B Service Parts Distpatch
Service Parts Delivery Confirmation (Supply Only) | Service Parts Delivery Confirmation (Supply Only)
Purpose
The Service Parts Delivery Confirmation module shall ensure that all supply-only service parts have been successfully delivered or collected before the order is marked as complete.
This module provides full traceability of service parts supplied to customers and ensures all delivery documentation is recorded within the CRM.
Rule SPD-001 – Service Parts Orders
This workflow shall apply to all Supply Only – Service Parts orders, including but not limited to:
Motors
Control Panels
MCC Units
Charger Packs
Batteries
Barrels
Bottom Rails
Guide Rails
Curtain Fabric
End Plates
Motor Brackets
ERBs
Audio Visual Warning Units
Obstruction Sensor Kits
Fire Reset Switches
Replacement Components
Spare Parts
Other Service Parts
Delivery Status
Each service parts order shall display one of the following statuses:
Awaiting Parts
Parts in Stock
Awaiting Dispatch
Ready for Collection
Out for Delivery
Delivered
Collected
Delivery Failed
Returned
Order Complete
Delivery Method
The CRM shall record the delivery method:
Customer Collection
IFS Delivery
External Courier
Direct from Supplier
Delivery Information
The following information shall be recorded:
Service Order Number
Customer
Project / Site
Delivery Address
Delivery Date
Courier / Delivery Company
Tracking Number
Driver (if IFS Delivery)
Vehicle (if IFS Delivery)
Delivery Confirmation
Before the order can be marked as Complete, the CRM shall confirm:
Parts have been delivered or collected.
Delivery date has been recorded.
Delivery method has been recorded.
Any delivery documents have been uploaded.
Delivery confirmation has been completed.
Supporting Documents
The CRM shall allow uploads of:
Delivery Note
Courier Tracking Confirmation
Proof of Delivery (POD)
Proof of Collection (POC)
Supplier Delivery Note
Customer Delivery Confirmation
Photographs (optional)
All documents shall be stored against the service order.
QR Code Confirmation (Optional)
Where IFS performs the delivery or customer collection, the Stores or Delivery Team may scan the Service Parts QR Code to automatically:
Mark the order as Delivered or Collected.
Record the date and time.
Record the user completing the action.
Notify the Office Team.
Update the Service Operations Dashboard.
Trigger invoice workflow where applicable.
Accounts Integration
Once delivery has been confirmed, the CRM shall:
Flag the order as Ready to Invoice (where applicable).
Notify the Accounts Team.
Update the order status to Completed once invoicing requirements have been met.
Record whether the order was prepaid or invoiced on account.
Dashboard Alerts
The Service Operations Dashboard shall highlight:
Service Parts Awaiting Dispatch
Service Parts Out for Delivery
Service Parts Awaiting Collection
Delivery Confirmations Outstanding
Orders Ready for Invoicing
Overdue Deliveries
Audit Trail
The CRM shall record:
Delivery method.
Delivery status changes.
Date and time of delivery or collection.
User confirming delivery.
Courier or driver details.
Uploaded delivery documents.
Invoice trigger.
All subsequent status updates.
This gives you a complete audit trail from parts ordered → dispatched → delivered/collected → invoiced, ensuring no supply-only service order is closed until the customer has actually received the parts. It also aligns the service parts workflow with the same level of traceability you're building into your installation and manufacturing modules.

## Stage 3 - Survey - Drawings
Stage 3 - Survey and Drawings
Additional Rules – Live Service (LS)
Survey Requirement
Field: Requires Survey
Field Type: Dropdown
Options:
Yes
Not Applicable
Rule:
If Yes is selected, the Live Service cannot progress until a Survey record has been completed.
If Not Applicable is selected, the Survey stage is automatically marked as N/A, and the project may proceed to the next stage.
Drawing Requirement
Field: Requires Drawings
Field Type: Dropdown
Options:
Yes
Not Applicable
Rule:
If Yes is selected, drawings must be uploaded and approved before the relevant work can proceed.
If Not Applicable is selected, the Drawing stage is automatically marked as N/A, and no drawing approval is required.
Workflow Logic
| Requires Survey | Requires Drawings | Workflow
| Yes | Yes | Complete Survey and Drawings before progressing.
| Yes | Not Applicable | Complete Survey only.
| Not Applicable | Yes | Drawings required without a survey.
| Not Applicable | Not Applicable | Skip the Survey & Drawings stage and continue to the next workflow stage.
Workflow Configuration
Survey Requirement
Field: Requires Survey
Field Type: Dropdown
Options:
Yes
System Manufactured from Drawings
Rule
Yes – The project must proceed to the Survey & Drawings (SD) stage before manufacture can begin.
System Manufactured from Drawings – No site survey is required. Manufacturing will proceed using the customer-approved drawings supplied for the project.
Distribution Type
Field: Distribution Type
Field Type: Dropdown
Options:
Supply Only – Customer Collection
Supply Only – IFS Delivery
Supply & Installation – Allocate to Installation Team
Rule
The selected Distribution Type determines the workflow after manufacturing:
Supply Only – Customer Collection
Project progresses to Stage 6A – Collection.
Customer is notified when the order is ready for collection.
Supply Only – IFS Delivery
Project progresses to Stage 6B – Delivery.
Delivery details, vehicle allocation and proof of delivery are managed within the Delivery module.
Supply & Installation – Allocate to Installation Team
Project progresses to Stage 6C – Installation.
The project is allocated to the Installation Team.
Installation dates, engineer allocation, RAMS, commissioning and handover are managed through the Installation module.
This is a nice way of designing it because two dropdowns drive the entire workflow:
1. Survey Requirement → Determines whether a survey is needed or manufacturing can proceed from customer drawings.
2. Distribution Type → Determines whether the finished product goes to Collection, Delivery, or Installation.

## Stage 4A - Ready for Prod LQ
Stage 4 Ready for Production LQ
| The CRM should generate documents based on the Distribution Type. | Component Parts Order (SERVICE -LS)
| Distribution Rules | Main Components
Motor CSV (L)
| Live Quotations (LQ) | Motor CSV (S)
Motor Control Card
| Distribution Type | Control Panel CSV
PCB Board Only
| Dropdown Options: | Barrel
End Plate
| 1. Supply Only – Customer Collection | Motor Bracket
| 2. Supply Only – IFS Delivery | Bottom Rail
| 3. Supply & Installation | Curtain Fabric
| Option 1 – Supply Only – Customer Collection | Power Components
| Automatically generate: | Charger Pack
| Production Specification | Battery Type (Dropdown)
Manufacturing Documentation
| Packing List | MLV Battery Set
| Box Labels | CSV Battery Set
| Pallet Labels (if applicable) | Other (Specify)
Collection Manifest
| Proof of Collection | Other Battery Description
| Do not generate: | Quantity
Installation Pack
Commissioning Documents
| Engineer Pack | Electrical & Control Components
Delayed Drop / Stage Drop
Maintenance Key Switch
| Option 2 – Supply Only – IFS Delivery | Emergency Retract Button (ERB)
Audio Visual Unit
| Automatically generate: | Obstruction Sensor Kit
| Production Specification | Mechanical Components
Manufacturing Documentation
| Packing List | Side Guide
| Box Labels | Headbox
| Pallet Labels (if applicable) | Guide Brushes
| Delivery Manifest | Guide Inserts
| Delivery Labels | End Caps
| Proof of Delivery | Bottom Rail End Caps
Fixings
| Do not generate: | Roller Bearings
Shaft Components
Installation Pack
Commissioning Documents
Engineer Pack
Consumables
Cable
| Option 3 – Supply & Installation | Cable Glands
Labels
| Automatically generate: | Warning Stickers
Cable Ties
| Production Specification | Fasteners
| Manufacturing Documentation | Miscellaneous Parts
Installation Pack
Engineer Pack
RAMS
| Site Drawings | Other Parts
Commissioning Forms
| Customer Handover Pack | Other Component (Specify)
Quantity
| Do not generate: | Unit Cost
Notes
Packing List
Proof of Collection
Proof of Delivery
Automation
The installation team will collect the equipment internally, so external dispatch paperwork is not required.
The CRM shall automatically:
Check stock availability.
| Live Services (LS) | Reserve stock where available.
Flag items requiring purchase.
| Live Services should have a different workflow. | Generate a Picking List for Stores.
Generate a Purchase Order for unavailable items.
| Component Parts Order | Allocate parts to the engineer or project.
Record all issued parts against the Live Service history.
| Every Live Service should include a Component Parts Order. | Update inventory when parts are issued or returned.
This records all components required for:
Planned Service
Reactive Call-Out
Repairs
Warranty Work
Replacement Parts
Fulfilment Type
Dropdown Options:
1. Engineer Collection
2. Engineer Delivery
3. Customer Collection
4. Customer Delivery
Automatically Generated Documents
Depending on the fulfilment type, the CRM should generate:
Engineer Collection
Component Parts Order
Internal Picking List
Engineer Delivery
Component Parts Order
Packing List
Delivery Note
Proof of Delivery (to engineer or site)
Customer Collection
Component Parts Order
Packing List
Proof of Collection
Customer Delivery
Component Parts Order
Packing List
Delivery Note
Proof of Delivery

## Step 4B - Reday for Prod LS
Stage 4 Ready for Production LS
Stage 4B – Ready for Production (LS)
Purpose
The Ready for Production (LS) stage ensures that all technical, operational, commercial and engineering requirements have been completed before service components are manufactured, picked from stores, purchased or issued to the engineering team.
This stage acts as the final review and approval process before the Live Service (LS) progresses into production, stores or engineer issue.
Live Service Information
Each record shall display:
Live Service Number (LS)
Original Service Number (S)
Customer
Project / Site
Site Address
Service Type
Priority
Assigned Service Coordinator
Current Workflow Status
Service Readiness
The Service Department shall complete and review:
Service Plan
Service Scope
Engineer Allocation
Planned Service Date
Estimated Duration
Return Visit Required
Commissioning Required
Target Completion Date
Site Access Requirements
The Office Team shall confirm:
Site Contact
Contact Telephone Number
Working Hours
Site Induction Requirements
Permit to Work Requirements
Security Clearance
Parking Information
Access Equipment Required
Special Site Instructions
RAMS & Engineering Documentation
The following documents shall be uploaded and linked to the LS record:
RAMS
Site Survey
Previous Service Reports
Previous Repair Reports
Previous Call-Out Reports
Previous Commissioning Certificates
Previous Photographs
Asset History
Approved Drawings
Wiring Schematics
Product Data Sheets
Manufacturer Instructions
Engineer Job Pack
Component Identification
The Service Department shall identify all required components.
Examples include:
Motors
Control Panels
MCC Units
Charger Packs
Batteries
Curtain Fabric
Barrels
Bottom Rails
Guide Rails
End Plates
Motor Brackets
ERBs
Audio Visual Warning Units
Obstruction Sensor Kits
Fire Reset Switches
Replacement Parts
Consumables
Other Components
Service Component Specification
The CRM shall generate the required documentation, including:
Service Component Parts Order Form
Stores Picking List
Purchase Order Request
Production Specification (if manufacture is required)
Fabric Cutting List (where applicable)
Fabrication Requirements
Powder Coating Requirements
Packing List
Financial Control
The Office and Accounts Teams shall manage:
Warranty / Chargeable Status
Customer Order Received
Quotation Approved
Deposit Required
Deposit Received
Purchase Orders Raised
Supplier Costs
Labour Costs
Parts Costs
Delivery Costs
Invoice Status
Payment Status
Commercial information shall not be visible to engineers.
Inspection Requests
The CRM shall allow inspection requests to be created for:
Internal QA Inspection
Technical Review
Management Approval
Customer Witness Inspection
Fire Engineer Inspection
Building Control Inspection
Final Quality Inspection
Ready for Production Checklist
The CRM shall display a live readiness checklist.
| Requirement | Status
| Service Plan Complete | ✓ / ✗
| RAMS Approved | ✓ / ✗
| Site Access Confirmed | ✓ / ✗
| Engineering Documents Uploaded | ✓ / ✗
| Previous Service History Reviewed | ✓ / ✗
| Components Identified | ✓ / ✗
| Component Specification Created | ✓ / ✗
| Stores Requirements Complete | ✓ / ✗
| Financial Review Complete | ✓ / ✗
| Inspection Requirements Complete | ✓ / ✗
| Ready for Production | ✓ / ✗
Workflow Automation
Once all mandatory requirements have been completed, the CRM shall automatically:
Mark the LS as Ready for Production.
Notify the Stores Department to pick stock.
Notify Production where manufactured components are required.
Generate all component order forms and production documentation.
Notify Purchasing where non-stock items are required.
Notify the Service Coordinator that the job is ready for engineer issue.
Progress the LS to the next operational stage.
Stage 4B = Ready for Production (technical review, stores, production and purchasing).
Stage 5 = Service Operations Dashboard (live execution and engineer management).

## Stage 5 - LS or LQ MFG Tracker
Stage 5 - Manufacturing (MFG Tracker)
Each individual curtain needs its own unique QR code. The operative scans the QR code with their phone when the curtain enters or leaves their department, and the CRM updates immediately.
Stage 5 – Manufacturing QR Tracking
Rule MFG-QR-001 – Individual Curtain QR Code
When the Production Pack is approved, the CRM shall generate a unique QR code for each individual curtain/system.
The QR code must be linked to:
Manufacturing job number
LQ or LS reference
Customer and project
Curtain/system number
Curtain location
Product type
Width and drop
Current manufacturing department
Current manufacturing status
QC record
For example, a project with three curtains will have three separate QR codes:
Curtain 1 — MFG260001-01
Curtain 2 — MFG260001-02
Curtain 3 — MFG260001-03
The QR code label should remain attached to that curtain or its production paperwork throughout manufacture.
Mobile Scanning Process
The operative does not need the full CRM installed on their phone. Scanning the QR code should open a secure, mobile-friendly page for that specific curtain.
The page should show:
Project reference
Curtain number and location
Current department
Current status
Previous completed stage
Available next actions
Start
Complete
Place on Hold
Report a Problem
Upload Photo
The operative selects the relevant action, and the CRM updates live.
Department Workflow
Each department should scan the same curtain QR code.
Booking / Production Release
On scan:
Confirm curtain received into production
Mark production release complete
Record operative, date and time
Fabrication
On arrival:
Select Start Fabrication
CRM status changes to Fabrication – In Progress
On completion:
Scan again
Select Complete Fabrication
Upload photograph where required
CRM records completion
Curtain becomes available to the next department
Assembly
Start Assembly
Complete Assembly
Upload assembly photos
Record any missing or damaged components
Electrical / Controls
Where applicable:
Start Electrical Assembly
Panel or controls fitted
Wiring completed
Electrical test completed
Quality Control
Start QC
Open the correct QC form
Complete checks
Upload photographs
Select Pass or Fail
Add comments and defects
A curtain that fails QC must not be marked ready for collection, delivery or installation.
Final Completion
Following a successful QC scan:
Curtain status changes to QC Passed
Manufacturing progress updates
The curtain is marked Manufacturing Complete
The project-level count updates, for example, from 2/3 to 3/3
Live CRM Updates
Every scan must update:
Curtain status
Current department
Overall project progress
Department workload
Manufacturing dashboard
Operations dashboard
Completion forecast
Remaining curtain count
Delays and alerts
For example:
Curtain 2 scanned by Fabrication
Status: Fabrication Complete
Completed by: Kieran
Date and time: 19 July 2026, 14:32
Next department: Assembly
Project progress: 2/3 curtains through fabrication
Scan Validation
The CRM should only display actions that are valid for the curtain's current stage.
For example:
An operative cannot complete Assembly before Fabrication is complete.
QC cannot begin before all required manufacturing stages are complete.
Manufacturing cannot be completed following a QC failure.
A failed curtain must be returned to the appropriate department for rework.
Only an authorised administrator or production manager can override the normal sequence.
Problems and Holds
When Report a Problem or Place on Hold is selected, the operative must enter:
Problem category
Description
Photograph
Parts required
Responsible department
Expected resolution date
The CRM shall:
change the curtain status to On Hold;
display an alert on the Manufacturing Dashboard;
notify the Production Manager;
retain the curtain's existing progress;
prevent it from progressing until the hold is cleared.
Audit Trail
Every QR interaction must record:
Curtain/system scanned
User or operative
Department
Action selected
Previous status
New status
Date and exact time
Device used
Photos uploaded
Comments
Any manager override
This gives you a live record of exactly who handled every curtain, when they handled it, what they completed, and where the curtain is now.
The QR code updates the information, but everyone in the business needs a clear project manufacturing view showing the live position of every curtain.
Add this under Stage 5 – Manufacturing (MFG Tracker):
Manufacturing Project Tracker
Rule MFG-002 – Shared Live Manufacturing View
The Manufacturing Tracker shall provide a live project-level view accessible to authorised office, production, contracts, operations and management users.
Each project must show:
MFG Number
LQ or LS reference
Customer
Project name
Number of curtains
Overall manufacturing progress
Required completion date
Distribution type
Current project status
Outstanding actions
Production priority
Individual Curtain Tracking
Each curtain within the project must appear as a separate row.
| Curtain | Location | Fabrication | Powder Coating | Assembly | Electrical | QC | Final Status
| Curtain 1 | Ground Floor Lobby | Complete | Complete | Complete | N/A | Passed | Ready
| Curtain 2 | Stair Core 1 | Complete | In Progress | Not Started | N/A | Pending | In Production
| Curtain 3 | Reception | Complete | Complete | On Hold | N/A | Pending | On Hold
The tracker must update automatically whenever a department scans the curtain QR code.
Status Indicators
Each department stage should display one of the following:
Not Started
Ready to Start
In Progress
Complete
On Hold
Failed
Rework Required
Not Applicable
The tracker should also display:
person completing the latest action;
date and time of the latest update;
number of curtains completed, for example 2/5;
number currently on hold;
number awaiting QC;
number ready for collection, delivery or installation.
Project Progress
The project-level progress should be calculated from the individual curtain records.
Example:
Overall manufacturing progress: 68%
Curtains complete: 3/5
Awaiting QC: 1
On hold: 1
Target completion date: 24 July 2026
A project must not show as Manufacturing Complete until every curtain is either:
QC Passed and complete; or
formally marked Not Applicable for a particular department.
Filters and Search
Users should be able to filter the Manufacturing Tracker by:
MFG number
LQ number
LS number
customer
project
current department
manufacturing status
priority
due date
assigned operative
distribution type
Access Permissions
Production Operatives
Can:
view assigned manufacturing jobs;
scan QR codes;
start and complete department tasks;
upload photos and report issues.
Production Manager
Can:
view all projects;
reallocate work;
place jobs on hold;
clear holds;
approve rework;
override a stage with a mandatory reason.
Contracts and Operations
Can:
view all manufacturing progress;
see delays and completion forecasts;
see which curtains are ready.
They should not be able to alter manufacturing completion records.
Management and Administrators
Can:
view all data;
access reports and KPIs;
review audit history;
make authorised corrections.
Dashboard Alerts
The shared tracker should highlight:
overdue projects;
missing materials;
curtains on hold;
failed QC;
rework required;
no update within the expected period;
jobs at risk of missing the installation, collection or delivery date.
That gives you one central live screen where everyone can open a project and see exactly where every individual curtain is in the manufacturing process.

## Stage 5 - LIVE MFG Tracker
Stage 5 - Central Production - Manufacturing - Live MFG Tracker
Stage 5 – Central Production – Manufacturing – Live MFG Tracker
Purpose
The Central Production – Manufacturing – Live MFG Tracker is the central live production management system for Insight Fire Solutions.
It provides a real-time overview of every project currently in manufacture, allowing Production, Contracts, Operations, Sales and Management to monitor progress from production release through to completion.
Every department updates the tracker by scanning the curtain's unique QR code, ensuring the CRM always reflects the live manufacturing status of every individual curtain.
Rule MFG-001 – Live Manufacturing Record
Every approved Production Specification shall automatically create a Live Manufacturing Record (MFG).
Each MFG record shall remain linked to:
Live Quotation (LQ)
Live Service (LS)
Production Specification
Individual Curtain Records
Asset Record (upon completion)
Central Manufacturing Dashboard
Each project shall display:
Project Information
MFG Number
LQ / LS Number
Customer
Project Name
Site
Number of Curtains
Distribution Type
Priority
Required Completion Date
Installation / Collection / Delivery Date
Overall Progress
Display:
Overall Manufacturing %
Curtains Complete
Curtains In Progress
Curtains On Hold
Curtains Awaiting QC
Curtains Ready
Estimated Completion Date
Example:
6 of 8 Curtains Complete
Overall Progress: 75%
Individual Curtain Tracker
Every curtain must have its own live manufacturing record.
Display:
Curtain Number
Curtain Location
Width × Drop
Product Type
Current Department
Current Status
Assigned Operative
Last Updated
QR Code Status
Manufacturing Departments
Each department shall update the curtain by scanning its QR code.
Departments:
Production Release
Stores / Components
Fabrication
Powder Coating
Sewing
Curtain Hanging
Assembly
Electrical Assembly
Quality Control
Packaging
Ready for Dispatch
Ready for Installation
Each department records:
Start
Complete
On Hold
Report Issue
Upload Photograph
Notes
QR Code Workflow
Every curtain shall have a unique QR code.
When scanned, the CRM shall:
Open the curtain record.
Display the current manufacturing stage.
Display the available actions.
Update the manufacturing tracker immediately after the operative submits an action.
Record the operative, date and time.
Upload photographs where required.
The project dashboard shall refresh automatically so all authorised users can see the latest manufacturing status.
Quality Control
QC shall include:
QC Checklist
Photographs
Pass
Fail
Rework Required
QC Notes
Inspector
Date
A curtain cannot move to the next stage until QC has been successfully completed.
Packaging & Dispatch Readiness
Once QC has passed, the CRM shall indicate whether the curtain is ready for:
Customer Collection
IFS Delivery
Installation Team
based on the project's Distribution Type.
Live Visibility
The following users shall have live access to the Manufacturing Tracker:
Production
Stores
Contracts
Operations
Sales
Management
Administrators
All users shall see the same live manufacturing information.
Dashboard Alerts
The Manufacturing Tracker shall highlight:
Projects behind programme
Curtains on hold
Missing components
Outstanding purchase orders
Failed QC
Rework required
Overdue manufacturing stages
Projects approaching installation, collection or delivery dates
Audit Trail
Every action shall record:
Curtain Number
Project Number
Department
Operative
Previous Status
New Status
Date and Time
Photographs Uploaded
Notes
Manager Overrides
One enhancement I'd recommend
Instead of just showing a list, make the Central Production – Manufacturing – Live MFG Tracker resemble a production board. Each project could expand to show all its curtains underneath, so at a glance you could see:
Project: LQ260045 – 7 Curtains – 5/7 Complete
Curtain 1 – Ready for Dispatch ✅
Curtain 2 – QC Passed ✅
Curtain 3 – Assembly 🔄
Curtain 4 – Powder Coating 🎨
Curtain 5 – On Hold ⚠️
Curtain 6 – Fabrication 🔧
Curtain 7 – Stores 📦
That gives everyone—from production to contracts—the same live view of exactly where every curtain is without opening multiple screens.

## Stage 6A - Cost. Collection
Stage 6 Customer Collection - Supply Only
Stage 6A – Customer Collection (Supply Only)
Rule COL-002 – Internal Collection QR Code
When a supply-only order is collected, the Stores Operative shall scan the project's Collection QR Code.
The QR code is for internal CRM processing and is not intended as a customer signature.
QR Code Scan
When scanned, the CRM shall automatically:
Update the project status to Collected.
Record the collection date and time.
Record the Stores Operative who released the goods.
Record the project as completed for collection.
Update the Operations Dashboard.
Accounts Automation
Immediately after the collection is confirmed, the CRM shall check the project's payment terms.
Payment Due Prior to Collection
If the project is marked Payment Prior to Collection = Yes:
The CRM shall:
Check whether payment has been received.
If payment has not been received:
Display a DO NOT RELEASE GOODS warning.
Prevent the collection from being completed until an authorised user overrides it.
Notify the Accounts Team.
Deposit Invoicing
If the payment schedule requires a deposit invoice after collection, the CRM shall automatically:
Flag the project for Deposit Invoice Required.
Place the project in the Accounts Dashboard.
Notify the Accounts Team that an invoice is ready to be issued.
Final Invoice
Where collection triggers the balance payment, the CRM shall automatically:
Flag Final Invoice Required.
Update the outstanding balance.
Notify Accounts.
Audit Trail
The CRM shall record:
Collection QR Code scanned.
Stores Operative.
Date and time.
Goods released.
Collection completed.
Accounts notification sent.
Invoice flag created.
Payment status at the time of collection.

## 6B - IFS Delivery Supply Only
Stage 6B – Distribution Type – IFS to Deliver (Supply Only) | Stage 6B – Distribution Type – IFS to Deliver (Supply Only)
Purpose
The IFS Delivery stage manages the delivery of completed supply-only orders by Insight Fire Solutions.
It ensures goods are correctly packed, allocated to a delivery vehicle, delivered to the customer and recorded within the CRM before the project is closed.
Rule DEL-001 – IFS Delivery
Only projects with the Distribution Type:
Supply Only – IFS to Deliver
shall progress to this stage.
Required Behaviour
When Manufacturing is marked Complete, the CRM shall automatically:
Move the project to the Delivery module.
Generate the delivery documentation.
Allocate the project for delivery scheduling.
Await Accounts Release Approval (if applicable).
Notify the Operations Team that the order is ready for delivery.
Delivery Information
Project Details
Delivery Number
MFG Number
LQ Number
Customer
Project Name
Site Address
Delivery Status
Delivery Details
Delivery Date
Delivery Time Slot
Delivery Driver
Vehicle
Delivery Contact
Customer Telephone
Delivery Notes
Special Access Instructions
Delivery Status
Dropdown:
Awaiting Accounts Approval
Awaiting Scheduling
Delivery Booked
Loaded
Out for Delivery
Delivered
Delivery Failed
Returned to Warehouse
Automatically Generated Documents
The CRM shall generate
Delivery Management
Delivery Method
Field Type: Dropdown
Options:
In-House Delivery (IFS Delivery Team)
External Delivery Company
If "In-House Delivery" is selected
The CRM shall record:
Driver Name
Vehicle
Delivery Date
Estimated Delivery Time
Delivery Notes
Fuel/Travel Cost (optional)
Internal Delivery Cost (optional)
If "External Delivery Company" is selected
The CRM shall record:
Delivery Company
Contact Name
Tracking Reference
Collection Date
Delivery Date
Estimated Delivery Time
Documents
The following documents can be uploaded:
Delivery Quotation
Delivery Cost Invoice
Delivery Confirmation
Proof of Delivery (if provided by the carrier)
Delivery Cost Recovery
Charge Delivery to Customer
Field Type: Yes / No
If "Yes"
The CRM shall:
Record the delivery cost.
Link the delivery cost to the project.
Flag the cost for inclusion on the customer invoice.
Notify the Accounts Team that delivery charges are to be invoiced.
If "No"
The CRM shall:
Record the delivery cost as an internal project cost only.
Exclude the delivery cost from the customer invoice.
Accounts Integration
The CRM shall display:
Delivery Cost
Customer Delivery Charge
Delivery Invoice Received (Yes / No)
Customer Invoice Raised (Yes / No)
Documents
The project record shall store:
Delivery Quote
Delivery Supplier Invoice
Customer Delivery Charge (if applicable)
Proof of Delivery
Delivery Notes
Automation
When delivery is marked as Completed, the CRM shall automatically:
Update the project status to Delivered.
Notify the Accounts Team.
Check whether the delivery cost is chargeable to the customer.
Flag the customer invoice if delivery is to be recharged.
Store all uploaded delivery documents against the project.
This also gives you a delivery cost history, so later can report on:
Total annual external courier costs.
Total in-house delivery costs.
Delivery costs recovered from customers.
Delivery costs absorbed by Insight Fire Solutions.
That will be valuable when reviewing project profitability and deciding whether to continue using external carriers or your own delivery team.

## Stage 6C - Install office View
Stage 6C - Installation Teams - Office View
Stage 6C – Installation Teams (Office View)
Purpose
The Installation Teams (Office View) module provides the Contracts, Operations and Management teams with complete visibility and control of all installation projects.
It manages engineer allocation, installation scheduling, access equipment, accommodation, documentation, commissioning status, project progress, commercial milestones and customer handover.
This module acts as the central office dashboard for all live installation projects.
Rule INS-001 – Installation Projects
Only projects with the Distribution Type:
Supply & Installation
shall progress to Stage 6C.
Installation Overview
Each installation project shall display:
LQ Number
MFG Number
Customer
Project Name
Site Address
Main Contractor
Client Contact
Site Contact
Planned Installation Date
Planned Completion Date
Current Installation Status
Overall Project Progress (%)
Installation Status
Dropdown
Awaiting Installation
Installation Scheduled
RAMS Pending
Awaiting Site Access
Awaiting Access Equipment
Materials Ready
Team Allocated
Installation In Progress
Installation Complete
Awaiting Commissioning
Commissioning Complete
Handover Complete
Return Visit Required
Project Complete
Engineer Allocation
The CRM shall allow allocation of:
Lead Engineer
Engineer 2
Engineer 3
Labourer(s)
Apprentice (optional)
Subcontract Engineer (optional)
For each person:
Name
Mobile Number
Email
Competency Status
Availability
Assigned Dates
The CRM shall prevent allocation of engineers with expired mandatory competencies where enforcement is enabled.
Installation Schedule
The Office Team shall manage:
Installation Start Date
Installation Finish Date
Working Hours
Night Works
Weekend Works
Number of Installation Days
Return Visit Dates
Commissioning Date
Access Equipment
The CRM shall record:
Scissor Lift
Cherry Picker
Tower Scaffold
Mobile Scaffold
MEWP
Podium Steps
Harness Equipment
Other
For each item:
Hire Company
Booking Reference
Delivery Date
Collection Date
Cost
Hire Documents
Delivery Confirmation
Collection Confirmation
Accommodation & Travel
Where applicable, the CRM shall record:
Hotels
Hotel Name
Address
Check-in Date
Check-out Date
Booking Reference
Total Cost
Travel
Vehicle
Fuel Costs
Flights
Ferry
Taxi
Parking
Toll Charges
Other Expenses
Supporting documents may be uploaded.
Installation Documentation
The Office Team shall upload and manage:
Approved Drawings
RAMS
Site Survey
Installation Instructions
Wiring Schematics
Control Panel Drawings
Product Data Sheets
Commissioning Documents
Customer Specifications
Site Instructions
Variation Orders
Client Correspondence
Materials & Equipment Checklist
The Office Team shall confirm:
Curtains Available
Control Panels Available
Motors Available
Accessories Available
Fixings Available
Consumables Available
Spare Parts Packed
Tools Confirmed
Commercial Controls
The CRM shall display:
Contract Value
Deposit Received
Stage Payment Status
Retention Amount
Variations
Outstanding Balance
Accounts Automation
The CRM shall automatically:
Flag stage payments due upon completion of agreed milestones.
Notify Accounts when an installation reaches an invoice trigger.
Flag projects awaiting commissioning where final invoices are dependent upon successful commissioning.
Display payment holds where applicable.
Commissioning Status
The CRM shall display:
Not Required
Awaiting Power
Awaiting Fire Alarm Interface
Ready for Commissioning
Commissioning Scheduled
Commissioning Complete
Return Visit Required
Health & Safety
The Office Team shall monitor:
RAMS Approved
Site Induction Required
Permits to Work
Asbestos Information
Site-Specific Risks
PPE Requirements
Emergency Contact Details
Live Dashboard
The dashboard shall display:
Installations This Week
Installations Today
Engineers on Site
Delayed Projects
Awaiting Commissioning
Return Visits
Outstanding RAMS
Outstanding Drawings
Access Equipment Due
Hotel Bookings
Stage Payments Due
Final Invoices Ready
Audit Trail
The CRM shall record:
Engineer allocations
Installation schedule changes
Document uploads
Commercial milestone changes
Commissioning updates
Return visits
Accounts notifications
User actions
Date and time of all changes
Future Integration
This Office View should work alongside your Stage 6D – Installation Teams (Field View). The office controls and monitors the project, while engineers on site update progress in real time through mobile devices. Every update made by the installation team automatically synchronises back to the Office View, giving Contracts, Operations and Management a live overview of every installation. This creates a single, real-time source of truth for all installation activities.
Off-Hire Trigger
The CRM shall automatically trigger an Off-Hire Required alert when any of the following occur:
Installation Status = Installation Complete
Installation Team confirms works are complete.
Project is placed on hold with no further access equipment required.
Installation dates are amended to an earlier completion date.
Dashboard Alerts
The Office Dashboard shall display:
🔴 Access Equipment Awaiting Off-Hire
Showing:
Project
Site
Hire Company
Equipment Type
Hire End Date
Estimated Daily Hire Cost
Days Overdue
Assigned Office User
Projects shall remain highlighted until the off-hire has been confirmed.
Off-Hire Record
For each item of hired equipment, the CRM shall record:
Equipment Type
Hire Company
Hire Reference
Delivery Date
Planned Off-Hire Date
Actual Off-Hire Date
Collection Date
Collection Reference
Collection Confirmed (Yes/No)
Off-Hire Requested By
Off-Hire Confirmed By
Supporting Documents
Notes
Documents
The following documents may be uploaded:
Off-Hire Request
Hire Company Confirmation
Collection Confirmation
Final Hire Invoice
Credit Note (if applicable)
Status
Each item shall display one of the following statuses:
Hire Booked
On Site
Off-Hire Required
Off-Hire Requested
Collection Scheduled
Collected
Hire Closed
Automatic Notifications
The CRM shall automatically notify the Office Team when:
An installation is completed and access equipment remains on hire.
The planned off-hire date has passed.
Equipment has not been collected within the expected timeframe.
A final hire invoice has been received (optional integration).
KPI Dashboard
Management shall be able to view:
Equipment currently on hire.
Equipment awaiting off-hire.
Overdue off-hires.
Total hire costs by project.
Average hire duration.
Total avoidable hire costs due to late off-hire.
This ties directly into your operations workflow. When the installation team marks a job as Installation Complete (or the office closes the installation), the project should automatically appear on the dashboard as "Off-Hire Required" until the office confirms that the access equipment has been collected and the hire has been closed. This creates a clear action list and helps prevent unnecessary hire charges.

## Stage 6D-Installation Field Vie
Stage 6D – Installation Teams (Field View) | Stage 6D – Installation Teams (Field View) | Job Sheets
Call Out Report
| Purpose | Installation Commissioning Sign off - Per Curtain
Repairs sign off per curtain
| The Installation Teams (Field View) provides engineers with a secure mobile and tablet-friendly portal to manage their assigned installation projects whilst on site. | Service and Miantenace per curtain
The portal shall allow engineers to access project information, installation documentation, update live progress, complete digital forms, upload photographs and synchronise updates directly with the Office View (Stage 6C).
Engineers shall only have access to projects assigned to them.
Rule INS-FLD-001 – Secure Engineer Login
Each engineer shall have their own secure login credentials.
The CRM shall display only:
Jobs assigned to the logged-in engineer.
Current installation projects.
Upcoming scheduled installations.
Return visits.
Commissioning visits.
Emergency call-outs (if assigned).
Engineers shall not have access to projects assigned to other engineers unless authorised.
My Installation Dashboard
The engineer dashboard shall display:
Today's Jobs
Tomorrow's Jobs
Upcoming Jobs
Return Visits
Commissioning Visits
Project Status
Installation Calendar
Each job shall display:
Project Name
LQ Number
Site Address
Site Contact
Contact Telephone Number
Installation Date
Estimated Duration
Current Status
Project Information
For each assigned project, engineers shall be able to view:
Project Details
Project Name
Site Address
Customer Name
Main Contractor
Site Contact
Site Telephone
Site Instructions
Special Installation Notes
Installation Documentation
Engineers shall be able to view and download:
Approved Drawings
Installation Drawings
Site Survey
RAMS
Wiring Schematics
Product Specifications
Installation Instructions
Packing List
Component List
Access Equipment Information
Health & Safety Information
Site-Specific Risk Assessments
Commercial Restrictions
The engineer portal shall not display:
Customer quotations.
Selling prices.
Labour costs.
Material costs.
Profit margins.
Payment schedules.
Customer invoices.
Internal commercial notes.
Any confidential commercial information.
Only operational information required to complete the installation shall be visible.
Individual Curtain Progress
Each curtain/system shall be listed separately.
For every curtain, the engineer shall be able to update:
Overall Status
Pending
In Progress
Installed
Awaiting Commissioning
Complete
On Hold
Installation Progress Checklist
The engineer shall confirm completion of:
Headbox Installed
Head Plates Installed
Barrel Installed
Curtain Fabric Installed
Guide Rails Installed
Bottom Rail Installed
Motor Installed
Motor Brackets Installed
End Plates Installed
Control Panel Installed
MCC Installed
ERBs Installed
Audio Visual Warning Units Installed
Obstruction Sensors Installed
Fire Reset Switch Installed
Fire Alarm Interface Connected
Optional Extras Installed
Electrical Connections Complete
Curtain Tested
Installation Complete
Each item shall include:
Complete
Not Applicable
Issue Identified
Digital Forms
The engineer shall complete project-specific forms including:
Pre-Installation Checklist
Installation Checklist
QA Inspection Form
Commissioning Certificate
Customer Sign-Off
Snagging Report
Variation Request
Defect Report
Daily Progress Report
Completed forms shall automatically save to the project record.
Photographic Records
Engineers shall be able to:
Take photographs directly from the mobile device.
Upload photographs from the device gallery.
Upload multiple photographs simultaneously.
Add captions or notes.
Assign photographs to a specific curtain or installation stage.
Suggested photo categories include:
Site Arrival
Before Installation
Headbox
Guide Rails
Motor
Control Panel
Electrical Connections
Fixings
Completed Installation
Commissioning
Customer Handover
Snagging / Defects
General Site Photos
All photographs shall automatically synchronise with the Office View.
Site Issues & Variations
Engineers shall be able to raise issues directly from site, including:
Missing Parts
Incorrect Drawings
Builder Delays
Access Issues
No Power
Fire Alarm Not Ready
Damaged Components
Health & Safety Concerns
Customer Variations
Other
Each issue shall allow:
Description
Priority
Photographs
Suggested Action
The Office Team shall receive an immediate notification.
Job Completion
When all assigned systems have been completed, the engineer shall select Complete Job.
The CRM shall automatically:
Record the completion date and time.
Update the project status.
Notify the Office Team.
Trigger any required commissioning workflow.
Trigger access equipment off-hire alerts where applicable.
Synchronise all forms, photographs and updates with the Office View.
Audit Trail
The CRM shall record all engineer activity, including:
Login and logout times.
Job start and finish times.
Status changes.
Individual curtain updates.
Form submissions.
Photograph uploads.
Issue reports.
Variation requests.
Customer signatures.
Date, time and user for every action.

## Installation Calender
Installation Calendar | Installation Calendar
Purpose
The Installation Calendar shall provide a central planning and scheduling system for all installation, commissioning, return visits and site activities.
The calendar shall enable the Office Team to allocate engineers, schedule works, monitor project progress and manage resources from a single location.
The calendar shall synchronise automatically with the Installation Teams (Office View) and Installation Teams (Field View).
Calendar Views
The calendar shall provide the following views:
Daily View
Weekly View
Monthly View
Engineer View
Project View
Customer View
Resource View
Commissioning View
Calendar Entries
Each calendar entry shall display:
LQ Number
MFG Number
Project Name
Customer
Site Address
Installation Type
Engineer(s) Assigned
Installation Status
Number of Systems
Number of Curtains
Estimated Duration
Colour coding shall identify the current status.
Example:
Blue – Scheduled
Green – In Progress
Grey – Complete
Orange – Awaiting Commissioning
Red – Delayed
Purple – Return Visit
Yellow – Awaiting Site Access
Installation Scheduling
The Office Team shall be able to:
Create installation bookings.
Allocate engineers.
Allocate labourers.
Schedule commissioning visits.
Schedule return visits.
Move installations by drag-and-drop.
Extend or shorten installation durations.
Reschedule projects.
Cancel bookings.
Duplicate recurring visits if required.
Engineer Allocation
Each booking shall record:
Lead Engineer
Engineer 2
Engineer 3
Labourer(s)
Apprentice
Subcontract Engineer
The CRM shall display engineer availability before allocation.
Where competency checking is enabled, engineers with expired mandatory training shall not be available for allocation.
Resource Planning
The calendar shall display allocated resources including:
Access Equipment
Company Vehicles
Hire Vehicles
Hotels
Specialist Equipment
Delivery Vehicles
Conflicts shall be highlighted automatically.
Access Equipment
Each installation booking shall display:
Equipment Type
Hire Company
Delivery Date
Collection Date
Off-Hire Date
Hire Status
When an installation is marked Complete, the CRM shall automatically highlight any access equipment that remains on hire and create an Off-Hire Required task until collection has been confirmed.
Hotels & Accommodation
Where accommodation is required, the calendar shall record:
Hotel Name
Booking Reference
Engineers Staying
Check-in Date
Check-out Date
Booking Status
Total Cost
Commissioning Planning
The calendar shall schedule:
Initial Commissioning
Return Commissioning
Witness Testing
Client Demonstrations
Fire Alarm Integration
Final Handover
Commissioning visits shall appear separately from installation visits while remaining linked to the same project.
Project Status
Each installation shall display:
Scheduled
In Progress
Installation Complete
Awaiting Commissioning
Commissioning Complete
Return Visit Required
Handover Complete
Status updates from engineers shall synchronise automatically with the calendar.
Automatic Notifications
The CRM shall automatically notify the Office Team when:
Engineers are allocated.
Installation dates change.
Engineer availability conflicts occur.
Access equipment requires booking.
Access equipment requires off-hire.
Hotels require booking.
Commissioning has not been scheduled.
Return visits are required.
Installation is completed.
Dashboard Integration
The Installation Calendar shall integrate directly with:
Stage 5 – Central Production (Live MFG Tracker)
Stage 6C – Installation Teams (Office View)
Stage 6D – Installation Teams (Field View)
Engineer Competency Records
Access Equipment Register
Vehicle Register
Accounts Dashboard
Permissions
Office / Contracts
Can:
Create installation bookings.
Allocate engineers.
Amend schedules.
Book hotels.
Book access equipment.
Schedule commissioning.
Reschedule projects.
Engineers
Can:
View assigned jobs.
View upcoming installations.
View project details.
Update installation progress.
Cannot:
Amend installation dates.
Reallocate engineers.
Modify commercial information.
Management
Can:
View all projects.
Amend schedules.
Override bookings.
Reallocate resources.
Monitor utilisation and performance.
Audit Trail
The CRM shall record:
Installation created.
Engineer allocations.
Schedule changes.
Resource allocations.
Hotel bookings.
Access equipment bookings.
Off-hire requests.
Commissioning bookings.
Return visits.
User making each change.
Date and time of every amendment.
Future Enhancements
The calendar should support drag-and-drop scheduling, automatic conflict detection, and filtering by engineer, customer, project, region or status. It should also provide utilisation reports showing engineer workloads, upcoming installation capacity, access equipment commitments, and commissioning schedules, giving the Operations Team a complete overview of all live and planned work. This will make the Installation Calendar the central planning tool for Insight Fire Solutions' installation operations.

## AST - Asset Register
AST – Asset Register | Asset Management (AST)
Step 1 – Create AST Asset
Purpose
The Create AST Asset process shall generate a unique Asset Record for every physical fire curtain, smoke curtain or associated system installed, commissioned or adopted under an Insight Fire Solutions service agreement.
Each physical system shall receive its own individual Asset Number (AST), creating a permanent record that will be used throughout the lifecycle of the asset.
Automatic Asset Creation
The CRM shall automatically create an Asset Record when:
An LQ project has been commissioned and handed over.
An existing third-party system is added to an Insight Fire Solutions maintenance contract.
A legacy asset is manually entered into the system.
Automatic Service Opportunity
Once an AST Asset has been created, the CRM shall automatically:
Calculate the next planned service date.
Add the asset to the Service Opportunities list.
Create a future reminder for the Service Department.
Automatically place the asset into the Service Quotes (S) pipeline when it reaches the configurable reminder period (for example, 90, 60 or 30 days before the service due date).
This ensures that every installed asset automatically becomes a future sales opportunity for the Service Department.
Next Service Due
Service Contract Status
Opportunity Status
Service Not Yet Due
Service Due Soon
Service Quote Required
Quote Created
Quote Sent
Follow-up Required
Won
Lost
Contract Active
Service Completed
Automatic Link to Service Quotes
When a Service Opportunity reaches the configured reminder period, the CRM shall:
Create a draft Service Quote (S), or place the asset into a "Quotes to Raise" queue.
Link the quote directly to the Asset Record (AST).
Carry forward all known asset information, including:
Customer details
Site address
Asset number
System details
Previous service history
Previous quotations
Contract history
Engineer notes
This removes the need for the Service Department to re-enter information manually.
Service Sales Pipeline
The CRM shall allow the Service Team to track every maintenance opportunity from quotation through to contract award.
Each Asset shall record:
Number of Service Quotes Issued
Number of Contracts Won
Number of Contracts Lost
Current Contract Status
Contract Start Date
Contract Expiry Date
Next Renewal Date
Total Lifetime Service Revenue
KPI Reporting
Management shall be able to report on:
Total Assets Installed
Assets Under Maintenance Contract
Service Quote Conversion Rate
Contracts Won
Contracts Lost
Assets Due for Renewal
Renewal Success Rate
Lifetime Revenue per Asset
This is one of the most valuable features of the CRM because it closes the loop:
LQ → MFG → Installation → AST → Service Opportunity → Service Quote (S) → Live Service (LS) → Service Completed → Next Service Due
That way, every installation automatically feeds your future service pipeline, giving your sales team a continuous list of maintenance opportunities to quote and follow up. It turns every installed curtain into a recurring business opportunity rather than a one-off sale.

## Asset Profile Life Cycle
Asset Profile & Life Cycle | Step 2 – Asset Profile & Life Cycle
Purpose
The Asset Profile & Life Cycle provides the complete operational history of each asset from installation through to decommissioning.
Every future service, repair, call-out, inspection and maintenance visit shall be recorded against the same Asset Record.
Asset Summary
Display:
Asset Number (AST)
Customer
Site
Building
Asset Description
Product Type
Fire Rating
Serial Number
Commissioning Date
Warranty Expiry
Service & Maintenance Status
Display:
Maintenance Contract Status
Current Service Contract
Next Service Due
Last Service Date
Service Level
Renewal Status
Asset Status & Risk
Display:
Operational Status
Warranty Status
Asset Condition
Risk Rating
Critical Asset Indicator
Open Defects
Outstanding Recommendations
Site Access Requirements
Store:
Site Contact
Telephone Number
Working Hours
Permit to Work
Site Induction
Security Requirements
Parking
Access Equipment
Special Instructions
Asset Documents
Store and link:
Drawings
O&M Manuals
Commissioning Certificates
Service Reports
Repair Reports
RAMS
Photographs
Product Data Sheets
Test Certification
Wiring Schematics
Linked Assets
Display:
Adjacent Systems
Linked Control Panels
Associated Fire Curtains
Smoke Curtains
Shared Equipment
Parent Project
Service History
Automatically record:
Planned Maintenance Visits
Call-Outs
Repairs
Component Replacements
Warranty Claims
Engineer Notes
Customer Sign-Offs
Asset Life Cycle Timeline
Display a complete chronological history including:
Installed
Commissioned
Handover
First Service
Repairs
Emergency Call-Outs
Upgrades
Component Replacements
Warranty Events
Contract Renewals
Decommissioned
Asset Metrics
Display live statistics such as:
Total Services Completed
Total Call-Outs
Total Repairs
Total Documents Stored
Total Components Replaced
Linked Assets
Age of Asset
Time Since Last Service
Days Until Next Service
Lifetime Revenue
Warranty Claims
Service Sales Integration
This is the feature I think will be invaluable for Insight Fire Solutions.
Every Asset Profile shall feed directly into the Service Quotes (S) module.
The CRM shall automatically track:
Assets approaching their next service date.
Service quotations that need to be raised.
Follow-up dates.
Quote status (Draft, Sent, Chasing, Won or Lost).
Whether the maintenance contract was secured.
This gives your Service Team a live pipeline of maintenance opportunities generated from assets you've already installed, allowing you to measure not only how many systems you've installed, but also how successfully you've converted those installations into ongoing service and maintenance contracts.

## Stock Control Sheet
Stock Control | Stock Control
Purpose
The Stock Control module shall provide a live inventory management system for all components, materials and consumables used by Insight Fire Solutions.
The system shall monitor stock levels in real time, track stock movements, allocate items to projects, manage purchasing requirements and maintain a complete audit trail of every stock transaction.
Stock shall be available for both:
Installation Projects (LQ)
Live Service Projects (LS)
Stock Item Record
Each stock item shall have its own unique inventory record.
Fields shall include:
Product Information
Stock Code
Component Description
Manufacturer
Category
Product Type
Unit of Measure
Location
Bin Number
Barcode / QR Code
Categories
Examples:
Motors
Tubular Motors
Motor Adaptors
Motor Brackets
Control Equipment
Control Panels
MCC Units
OCB Boards
Timer Relays
Chargers
Electrical
Batteries
ERBs
Fire Alarm Interfaces
Audio Visual Units
Beacons
Sounders
Reset Switches
Key Switches
Curtain Components
Curtain Fabric
Bottom Rails
Barrels
End Plates
Guide Rails
Fixings
Bolts
Anchors
Screws
Rivets
Chemical Resin
Consumables
Cable
Heat Shrink
Labels
Packaging
Foam
Wrapping
Pallets
Live Stock Levels
The CRM shall display:
Current Stock
Allocated Stock
Available Stock
On Order
Reserved
Minimum Level
Maximum Level
Reorder Level
Stock Allocation
Stock may be allocated to:
LQ Projects
LS Projects
MFG Jobs
Service Vans
Engineers
Warranty Stock
Demonstration Stock
Once allocated, the available quantity shall automatically reduce.
Stock Transactions
Every stock movement shall be recorded.
Transaction Types:
Goods Received
Goods Issued
Allocated to Project
Returned to Stores
Damaged
Scrapped
Warranty Replacement
Stock Adjustment
Stock Transfer
Engineer Van Issue
Engineer Van Return
Purchasing Integration
If stock falls below the minimum level, the CRM shall automatically:
Flag Low Stock
Recommend Purchase Order
Notify Purchasing
Display affected projects
QR Code / Barcode
Every stock item may be assigned a QR code or barcode.
Scanning shall allow users to:
Receive stock
Allocate stock
Issue stock
Return stock
Complete stock takes
Locate stock
Stock Locations
The CRM shall support multiple locations.
Examples:
Main Stores
Production
Powder Coating
Electrical Department
Engineer Van 1
Engineer Van 2
Engineer Van 3
Off-Site Warehouse
Project Allocation
Each stock item shall display:
Project Number
Customer
Quantity Allocated
Quantity Issued
Quantity Returned
Stock Take
The CRM shall support:
Full Stock Take
Rolling Stock Take
Department Stock Take
Van Stock Take
Differences shall automatically generate investigation records.
Dashboard
The Stock Control Dashboard shall display:
Total Stock Value
Low Stock Items
Out of Stock Items
Items Awaiting Delivery
Reserved Stock
Goods Received Today
Goods Issued Today
Stock Adjustments
Purchase Orders Outstanding
Permissions
Stores
Can:
Receive stock
Issue stock
Allocate stock
Complete stock takes
Print labels
Purchasing
Can:
Create Purchase Orders
Receive supplier deliveries
Update supplier pricing
Production
Can:
Request stock
Issue production components
Return unused items
Engineers
Can:
View allocated stock
Request replacement parts
Return unused components
Cannot:
Adjust stock quantities
Audit Trail
The CRM shall record:
User
Date
Time
Component
Quantity
Transaction Type
Project Reference
Engineer (if applicable)
Reason for Adjustment
Integration with the CRM Workflow
The Stock Control module shall integrate with:
Stage 4A – Ready for Production (LQ) (installation components)
Stage 4B – Ready for Production (LS) (service components)
Stage 5 – MFG Tracker (manufacturing consumption and finished goods)
Purchasing (automatic replenishment)
Stores (goods in/out)
Engineer Van Stock (field inventory)
Accounts (stock valuation and cost reporting)
This creates a single source of truth for inventory, ensuring that every movement—from supplier receipt to installation or service—is tracked accurately across the entire business.

## Engineer Portal
Engineer Portal & Self-Service Profile | Engineer & Contractor Portal (Self-Service Profile)
This covers:
Internal employees
Subcontract engineers
Labour-only operatives
Specialist contractors
Every person who may be allocated to an installation, service, repair or commissioning job has their own secure profile.
Purpose
The Engineer & Contractor Portal shall provide a secure self-service area where engineers and subcontractors can maintain their own profile, qualifications, competencies and supporting documentation.
The portal shall reduce office administration by allowing individuals to update their own records, while all changes remain subject to review and approval by the Office or Compliance Team.
The portal shall also provide automated reminders to both the individual and Insight Fire Solutions when qualifications, licences or competencies are approaching expiry.
Dual Notification System
One feature I'd definitely build in is that reminders go to both sides.
Engineer / Contractor Notifications
The individual shall receive notifications when:
CSCS expires soon.
PASMA expires soon.
IPAF expires soon.
SSSTS/SMSTS expires soon.
First Aid expires soon.
Driving licence check due.
Medical or occupational assessment due (if applicable).
Site approval expires.
Manufacturer competency review due.
The portal shall allow them to:
Upload the renewed certificate.
Book training (optional).
Update their profile.
View what is outstanding.
Office Notifications
At the same time, the Office Dashboard shall receive the same alerts.
For example:
Qualifications Expiring Within 90 Days
John Hazel – PASMA expires in 87 days
Kevin Clarke – IPAF 3A expires in 42 days
John iFix – CSCS expires in 19 days
The Operations or Compliance Team can then contact the engineer to ensure renewal is arranged before it affects work allocation.
Office Dashboard
The dashboard should show live compliance information such as:
Qualifications
Expired qualifications
Expiring within 90 days
Expiring within 60 days
Expiring within 30 days
Awaiting verification
Renewal documents uploaded
Renewals awaiting approval
Competency
Missing competencies
Manufacturer approvals
Installation competencies
Service competencies
Commissioning competencies
Engineer Status
Active
Available
On holiday
Training
Suspended
Documents outstanding
Engineer Dashboard
Each engineer only sees their own information.
For example:
My Qualifications
✅ CSCS
✅ PASMA
⚠ IPAF expires in 42 days
⚠ First Aid expires in 18 days
My Competencies
Fire Curtains
Smoke Curtains
Fire Doors
Fire Shutters
Installation
Service
Repairs
Commissioning
My Jobs
Upcoming Installations
Upcoming Services
RAMS
Drawings
Job Packs
Certificates to Complete
Automatic Allocation Rules
Even if an engineer ignores the reminders, the CRM shall continue to protect the business.
If a qualification expires, the system shall automatically prevent allocation to any job requiring that qualification until a valid, verified replacement has been approved.
Approval Workflow
1. Engineer uploads renewed certificate.
2. Office receives notification.
3. Compliance verifies the document.
4. Qualification status changes to Verified.
5. Expiry reminders reset automatically.
6. Engineer becomes fully available for allocation again.
I would also add a Compliance Score for each engineer or contractor. For example:
🟢 100% Compliant – All qualifications current and verified.
🟡 Warning – One or more qualifications expire within 30 days.
🔴 Non-Compliant – One or more mandatory qualifications have expired or are awaiting verification.
This gives the office an instant visual indication of who is ready to work and who needs attention, making it much easier to manage both your in-house engineers and subcontractors while ensuring you only allocate compliant personnel to jobs.
Availability & Holiday Management
Purpose
The Engineer & Contractor Portal shall allow each engineer or contractor to manage their own availability, planned leave and working preferences.
This information shall synchronise directly with the Installation Calendar and Service Calendar, allowing the office to allocate work based on real-time availability.
Holiday Requests
Each engineer or contractor shall be able to submit:
Annual Leave
Planned Holiday
Personal Leave
Training Days
Medical Appointments
Unavailable Dates
Company Shutdown
Other Absence
Each request shall include:
Start Date
End Date
Reason (optional)
Notes
Approval Workflow
Depending on the engineer type:
Internal Employees
Holiday requests shall be submitted to the Office for approval.
The Office can:
Approve
Reject
Request changes
The engineer shall receive a notification once the request has been processed.
Subcontractors
Subcontractors shall simply record the dates they are unavailable.
These dates will automatically block work allocation but do not require holiday approval.
Availability Calendar
Each engineer shall have a personal calendar showing:
Assigned Installation Jobs
Service Visits
Call-Outs
Holidays
Training
Days Unavailable
Available Days
Integration with Installation & Service Calendars
The portal shall synchronise with the office calendars.
When allocating work, the CRM shall automatically check:
Engineer availability.
Approved holiday.
Training commitments.
Existing job allocations.
Working time conflicts.
Maximum travel commitments (if configured).
Unavailable engineers shall not be available for allocation unless an authorised manager overrides the restriction.
Office Resource Planner
The office shall have a live resource view displaying:
Available Engineers Today
Engineers on Holiday
Engineers in Training
Engineers Already Allocated
Engineers Unavailable
Engineers Available Next Week
Engineers Available Next Month
The planner shall allow filtering by:
Qualifications
Product Competencies
Manufacturer Competencies
Region
Employment Type
Availability
Engineer Dashboard
Each engineer shall be able to:
View upcoming jobs.
View approved holidays.
Request annual leave (employees).
Record unavailable dates (subcontractors).
View training bookings.
See qualification expiry reminders.
Update their profile and upload renewed certificates.
Smart Job Allocation
When a job is being planned, the CRM should check everything automatically before allowing the allocation:
✅ Engineer is available.
✅ Engineer is not on holiday.
✅ Engineer holds the required qualifications.
✅ Engineer is authorised for the product/manufacturer.
✅ Qualifications remain valid for the job dates.
✅ Travel and scheduling do not conflict with existing commitments.
This effectively turns the Engineer & Contractor Portal into a complete resource management system, where availability, competency and compliance all work together. It means your Installation Calendar won't just show who is free—it will show who is both free and fully qualified for the specific job you're planning.
| CSCS | PASMA | IPAF 3A | IPAF 3B | SSSTS | First Aid | Driving
| Valid | Valid | Valid | Expired | Valid | Valid | Approved
| Valid | Not Held | Valid | Valid | Not Held | Expiring | Approved
| Valid | Valid | Not Held | Not Held | Valid | Not Held | Check Due

## Test Report Valid Dates
Test Reports & Certification Management | Traffic Light Compliance Monitoring
Purpose
The CRM shall automatically monitor the review dates, validity dates and expiry dates of all technical documents, including fire test reports, assessment reports, classifications, certifications and supporting documentation.
A traffic light system shall provide a visual indication of each document's current status, allowing the Technical Team to identify documents requiring attention before they expire or require review.
Traffic Light Status
| Status | Colour | Meaning
| Current | 🟢 Green | Document is valid and no action is currently required.
| Review Approaching | 🟡 Amber | Review or expiry date is approaching. Planning should begin for renewal or assessment.
| Action Required | 🟠 Orange | Document requires immediate attention. Assessment or review should be commissioned.
| Expired | 🔴 Red | Document has expired or passed its review date. Immediate action required.
| Superseded | ⚫ Grey | Document has been replaced by a newer version and is retained for historical purposes only.
Configurable Warning Periods
The warning periods shall be configurable by Insight Fire Solutions.
For example:
🟢 Green – More than 180 days remaining.
🟡 Amber – 180 to 90 days remaining.
🟠 Orange – 90 to 30 days remaining.
🔴 Red – Less than 30 days remaining or expired.
These time periods should be configurable within the CRM to suit business requirements.
Dashboard Alerts
The Technical Dashboard shall display:
Fire Test Reports Expiring
Assessments Due for Review
Classification Reports Requiring Renewal
UKCA Documents Due
Certifications Expiring
Documents Awaiting Technical Review
Each item shall display its current traffic light status and the number of days remaining.
Automatic Notifications
The CRM shall automatically notify nominated users when a document enters a new warning stage.
For example:
🟡 Amber: "Assessment Report AR-102 has 180 days remaining."
🟠 Orange: "Assessment Report AR-102 has 30 days remaining. Renewal should now be arranged."
🔴 Red: "Assessment Report AR-102 has expired."
Notifications may be sent to:
Technical Manager
Compliance Team
Operations Manager
Other authorised users
Dashboard Summary
The dashboard should provide an at-a-glance summary, for example:
🟢 Current: 186 documents
🟡 Review Due Soon: 12 documents
🟠 Immediate Action Required: 4 documents
🔴 Expired: 1 document
⚫ Superseded: 27 archived documents
This would give you an instant overview of the health of your technical library and help ensure that assessments and renewals are commissioned well before they become critical.